## Service Rings
Category | # | Services (sorted alphabetically) | Status | SLA | O365 Req | Cores | Storage (TB) | Ring Owner | [5 empty] | Updated | Trend | Comp. Grade | BCDR | Vs AWS | Established | [7 empty] | Emerging |  |  | Incubation | [6 empty] | Sovereign |  |  |  | Preview/Plan
[9 empty] | Classification Metrics | [9 empty] | United States (→) R0:80 -> 80% R1: 100 -> 100% | [5 empty] | Europe (→) R0: 90 -> 90% R1: 100 -> 100% |  | APAC ( → ) R0: 90 ->90% R1: 97-> 97% |  | LATAM ( ↑ ) R0: 80 -> 80% R1: 76->79% | Japan ( → ) R0: 90 -> 90% R1: 89 -> 89% |  | Australia ( ↑ ) R0: 70 -> 80% R1: 86 ->92% |  | India ( ↑ ) R0: 70 -> 70% R1: 63 -> 72% |  |  | China (↑) R0: 70 -> 70% R1: 52 -> 52% |  | US Gov ( ↑ ) R0: 50 -> 60% R1: 38 -> 46% |  | Canada (→) |  | Germany (→) |  | UK
[9 empty] | Core Azure Infrastructure? | Required by major 1st Party? (>100K Servers or > $100M Rev) | Stores Customer Data? | Global/Regional | Azure non ring 0 Pre-reqs | [5 empty] | US E (BL) | US E 2 (BN) | US N Centl (CH) | US Centl (DM) | US S Centl (SN) | US W (BY) | EU N (DB) | EU W (AM) | SE Asia (SG) | E Asia (HK) | BR S (CPQ) | JP E (TYO) | JP W (OSA) | AU E (SYD) | AU SE (MEL) | IN S (MAA) | IN Centl (PNQ) | IN W (BOM) | CN E (SHA) | CN N (BJB) | US Gov IA (DM) | US Gov VA (BN) | Can Centl (YTO) | Can East (YQB) | GER Centl (FRA) | GER NE (LEJ) | UK 1 | UK 2
Ring 0 | 1 | Azure Resource Manager | GA | 99.95 | Y | 202 | 35 | Charles Lamanna | Yes | Yes | Yes | Regional |  | 2015-09-07 | ↑ | D |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Nov | Nov | Jan | Jan
| 2 | Cloud Services | GA | 99.95 | Y | 6340 | 0 | George Moore | Yes | Yes | Yes | Regional |  | 2015-09-01 | → | D |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Nov | Nov | Jan | Jan
| 3 | Key Vault | GA | 99.9 | Y | 272 | 1 | Sumedh Barde | No | No | Yes | Regional |  | 2015-09-17 | ↑ | A |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Jan | Jan | Jan | Jan | Jan | Dec | Dec | Q1-16 | Q1-16 | Q1-16 | Q1-16
| 4 | Pilotfish | Internal |  | Y | NA | 0 | Darin Zhen | [5 empty] | 2015-09-01 | → |  |  | - | Nov | ü | ü | ü | Nov | ü | ü | ü | ü | ü | Q2-16 | Dec | Q1-16 | Dec | Q2-16 | Q2-16 | Q1-16 | Q2-16 | Q1-16 | Q1-16 | Q2-16 | Q2-16 | Q1-16 | Q1-16 | Q1-16 | Q1-16
| 5 | SQL Database | GA | 99.9 | Y | 4800 | 0 | Sherif Mahmoud | Yes | Yes | Yes | Regional |  | 2015-09-01 | → | B |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Dec | Dec | Jan | Jan
| 6 | Storage | GA | 99.99 | Y | NA | 0 | Leonidas Rigas | Yes | Yes | Yes | Regional |  | 2015-09-01 | → | D |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Nov | Nov | Jan | Jan
| 7 | Storage - Premium (XIO) | GA | 99.99 | N | NA | 0 | Sirius Kuttiyan | Yes | No | Yes | Regional |  | 2015-09-15 | → | A |  | - | Oct | ü |  | Oct | Q1-16 | ü | Oct | ü | ü | Nov | Q1-16 | ü | ü | ü | Nov | Dec | Dec | Q1-16 | ü | Jan | Dec | Nov | Q1-16 | Q1-16 | Q1-16 | Q1-16
| 8 | Virtual Machines (A1 - A7) | GA | 99.95 | Y | NA | 0 | Drew McDaniel | Yes | Yes | Yes | Regional |  | 2015-09-01 | → | D |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Nov | Nov | Jan | Jan
| 9 | Virtual Machines (D) | GA | 99.95 | Y | NA | 0 | Drew McDaniel | Yes | Yes | Yes | Regional |  | 2015-09-18 | → | D |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Dec | Oct | Nov | Nov | Jan | Jan
| 10 | Virtual Network | GA | 99.9 | Y | 20 | 0 | Henry Lee | Yes | Yes | No | Regional |  | 2015-09-01 | → | D |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Nov | Nov | Jan | Jan
Ring 1 | 11 | Active Directory* | GA | 99.9 | Y | NA | 0 | Philippe Signoret | No | Yes | No | Global |  | 2015-09-01 | → | D |  | ↑ | ü |  | ü |  | ü |  | ü | ü | ü | ü | [8 empty] | ü | ü | ü | ü |  |  | Jan | Jan
| 12 | API Management | GA | 99.95 | N | 50 | 1 | Kedar Joshi | No | No | Yes | Regional | Service Bus, Traffic Manager | 2015-09-01 | → | A |  | ↑ | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Oct | Oct | Oct | Dec | Dec | H1-16 | H1-16 | Q1-16 | Q1-16 | Q1-16 | Q1-16
| 13 | Application Gateway | GA | 99.9 | N | 30 |  | Amit Srivastava | [5 empty] | 2015-09-01 | → |  |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Dec | Dec | Q1-16 | Q1-16
| 14 | Automation | GA | 99.9 | N | 110 |  | Gary Keong | No | No | Yes | Regional |  | 2015-09-18 | ↑ | A |  | - |  | ü |  |  | ü | Oct |  | ü | ü |  | Q1-16 | ü |  | Q1-16 | Q1-16 |  |  |  | Dec | ü |  | ü | Q1-16 | Q1-16 | Q1-16 | Q1-16
| 15 | App Service | GA | 99.95 | Y | NA | 0 | Omar Khan | No | No | Yes | Regional |  | 2015-09-01 | → | - |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Oct | Oct | Oct | Dec | Dec | Q1-16 | Q1-16 | Dec | Dec | Q1-16 | Q1-16
| 16 | Web App | GA | 99.95 | Y | 350 | 25 | Stefan Schackow | No | No | Yes | Regional |  | 2015-09-30 | → | C |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Oct | Oct | Dec | Dec | Q1-16 | Q1-16
| 17 | Mobile App | GA | 99.95 | Y |  | 0 | Kirill Gavrylyuk | No | No |  | Regional | Ibiza | 2015-09-01 | → | C |  | ↑ | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Oct | Oct | Oct | Dec | Dec | Q1-16 | Q1-16 | Dec | Dec | Q1-16 | Q1-16
| 18 | API App | GA | 99.95 | N |  | 0 | Kamal Bhatt | No | No |  | Regional |  | 2015-09-01 | → | A |  | ↑ | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Dec | Dec | Q1-16 | Q1-16 | Dec | Dec | Q1-16 | Q1-16
| 19 | Logic App | GA | 99.95 | N | 16 |  | Stephen Siciliano | No | No |  | Regional | Ibiza | 2015-09-01 | → | A |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Oct | Oct | Oct | Dec | Dec | Q1-16 | Q1-16 | Dec | Dec | Q1-16 | Q1-16
| 20 | Backup | GA | 99.9 | Y | 450 |  | Giridhar Mosay | No | No | Yes | Regional |  | 2015-09-14 | ↑ | B |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Dec | Dec | Q1-16 | Q1-16
| 21 | Batch | GA | 99.9 | Y | 63 |  | Alex Sutton | No | Yes | No | Regional |  | 2015-09-01 | → | D |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Q1-16 | Q1-16 | Dec | Dec | Dec | Dec
| 22 | CDN* | GA | 99.9 | N | NA |  | Anton Kucer | No | No | Yes | Regional |  | 2015-09-22 | → | A |  | → | ü |  | ü |  | ü | ü | ü | ü | ü | ü | Nov | ü | ü | ü | ü | Dec | Dec | Dec | ü | ü |  |  |  |  | ü | ü
| 23 | CRM Online | GA | 99.9 | N |  |  | Jean Gabarra | [5 empty] | 2015-09-01 | → |  |  | - | ü |  |  |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | H1-16 | H1-16 |  |  |  | ü | ü | H1-16 | H1-16 | H2-16 | H2-16
| 24 | Document DB | GA | 99.95 | N | 5760 | 0 | Stephen Baron | No | No | Yes | Regional |  | 2015-09-22 | ↑ | A |  | → | ü |  |  | Q1-16 | Q1-16 |  | ü | ü | ü | ü | Dec | Dec | Dec | ü | ü | ü | ü | ü
| 25 | EMS | GA | 99.9 | NA | NA |  | NA | No | Yes |  | Global |  | 2015-09-30 | → | - |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü |  |  | Q2-16 | Q2-16 | ü | ü |  |  | ü | ü
| 26 | Active Directory Premium* | GA | 99.9 | N | NA |  | Philippe Signoret | No | No | No | Global |  | 2015-09-30 | → | A |  | ↑ | ü |  | ü |  | ü |  | ü | ü | ü | ü | [8 empty] | H2-16 | H2-16 | Q2-16 | Q2-16
| 27 | Azure Rights Management* | GA | 99.9 | Y | NA |  | Gagan Gulati | No | Yes | Yes | Global |  | 2015-09-01 | → | D |  | ↑ | ü |  | ü |  |  | ü | ü | ü | ü | ü | [10 empty] | Q1-16 | Q1-16
| 28 | Intune* | GA | 99.9 | N | NA |  | Scot Nunes | No | No | No | Global |  | 2015-09-30 | → | C |  | - |  |  | ü | ü | ü |  | ü | ü | ü | ü | [10 empty] | Q2-16 | Q2-16 |  |  | Q1-16 | Q1-16
| 29 | Event Hubs | GA | 99.9 | N | 0 |  | Arun Dsouza | No | No | Yes | Regional |  | 2015-09-01 | → | A |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Dec | Dec | Q1-16 | Q1-16
| 30 | ExpressRoute | GA | 99.9 | Y | NA |  | Charley Wen | No | Yes | No | Regional |  | 2015-09-01 | → | B |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Nov | ü | ü | ü |  | ü | Dec | Oct | ü | ü | Jan | Jan | Q1-16 | Q1-16
| 31 | HDInsight | GA | 99.9 | N | 1000 | 0 | Andrea Peggion | No | No | No | Regional |  | 2015-09-01 | → | B |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü |  | ü |  | ü | ü |  |  | Feb | Feb | Q1-16 | Q1-16
| 32 | Machine Learning | GA | 99.95 | N | 3800 |  | Ted Way | No | No | Yes | Regional |  | 2015-09-12 | ↑ | A |  | → |  |  |  |  | ü |  |  | ü | ü |  | Dec | H1-16 | H1-16 | H1-16 | H1-16 | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 | H2-16
| 33 | Media Services | GA | 99.9 | Y | 1400 | 0 | Bo Hong | No | Yes | Yes | Regional | Batch | 2015-09-01 | → | C |  | ↑ | ü |  |  |  |  | ü | ü | ü | ü | ü | Oct | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Jan | Jan | Q1-16 | Q1-16
| 34 | Multi-factor Authentication* | GA | 99.9 | Y | NA |  | Shawn Bishop | No | Yes | Yes | Global |  | 2015-09-01 | → | D |  | - |  | ü | [16 empty] | Dec | Dec | ü | ü
| 35 | Notification Hubs | GA | 99.9 | Y | 12 |  | Scott Seely | No | Yes | No | Regional | Service Bus, Traffic Manager | 2015-09-01 | → | C |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Dec | Dec | Q1-16 | Q1-16
| 36 | Portal - Current* | GA |  | Y | NA |  | Vivek Dalvi | No | Yes |  | Global |  | 2015-09-01 | → | D |  | → |  |  | ü |  | ü | [13 empty] | ü | ü | ü | ü
| 37 | Portal - Ibiza | Preview |  | Y | 64 |  | Vivek Dalvi | No | Yes |  | Global |  | 2015-09-01 | → | A |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Q1-16 | Q1-16 | Q1-16 | Q1-16 |  |  | Jan | Jan
| 38 | Power BI | GA | 99.9 | Y | 488 |  | Adam Wilson | No | Yes | Yes | Regional |  | 2015-09-01 | → | B |  | - |  | ü | ü | ü |  | ü | ü | ü | ü |  | Nov | Dec | Dec | Dec | Dec | Dec | Dec | Dec | H2-16 | H2-16
| 39 | Redis Cache | GA | 99.9 | Y | 16 |  | Pranav Rastogi | No | Yes | Yes | Regional |  | 2015-09-18 | ↑ | A |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | [8 empty] | ü | ü | ü | ü | Dec | Dec | Q1-16 | Q1-16 | bar: Nov to Dec
| 40 | RemoteApp | GA | 99.9 | N | 18 |  | Tristan Scott | No | No | Yes | Regional |  | 2015-09-01 | → | A |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Oct | Oct | Oct |  |  |  |  | Dec | Dec
| 41 | Search | GA | 99.9 | N | 300 |  | Liam Cavanagh | No | No | Yes | Regional |  | 2015-09-01 | → | A |  | → | ü |  | ü |  | ü | ü | ü | ü | ü | ü | [12 empty] | Q1-16 | Q1-16 | bar: Nov; Dec to Dec; Dec
| 42 | Scheduler | GA | 99.9 | Y | 16 | 1 | Kevin Lam | No | Yes | No | Regional |  | 2015-09-01 | → | B |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | [8 empty] | ü | ü | ü | ü | Dec | Dec | Dec | Dec | bar: Nov to Dec
| 43 | Service Bus | GA | 99.9 | Y | 124 | 1 | Arun Dsouza | No | Yes | Yes | Regional |  | 2015-09-01 | → | D |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | [8 empty] | ü | ü | ü | ü | Dec | Dec | Q1-16 | Q1-16 | bar: Nov to Dec
| 44 | Site Recovery | GA | 99.9 | N | 425 |  | Sneha Magapu | No | No | Yes | Regional |  | 2015-09-30 | → | B |  | ↑ | ü |  |  |  |  | ü | ü | ü | ü | ü | [8 empty] | ü | ü | Oct | Oct | Dec | Dec | Q1-16 | Q1-16 | bar: Nov to Dec
| 45 | Storage - Files | GA |  | N |  |  | Jason Tang | No | No |  | Regional |  | 2015-09-29 | ↑ | - |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | [8 empty] | Oct | Oct | Oct | Oct | bar: Nov to Dec
| 46 | StorSimple | GA | 99.9 | N | 50 | 200 | Manjula Kumar | No | No | Yes | Regional |  | 2015-09-01 | → | A |  | → | ü |  |  |  |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Oct | Oct | Oct | ü | ü | ü | ü | Q1-16 | Q1-16 | Q1-16 | Q1-16
| 47 | Stream Analytics | GA | 99.9 | N | 28 |  | Zafar Abbas | No | No |  | Regional |  | 2015-09-08 | ↑ | A |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü |  | Oct |  | ü | ü |  |  | Q1-16 | Q1-16 | Q1-16 | Q1-16
| 48 | Traffic Manager* | GA | 99.99 | Y | NA |  | Jonathan Tuliani | No | Yes | No | Global |  | 2015-09-01 | → | D |  | → |  |  | ü |  | ü | [13 empty] | ü | ü | ü | ü |  |  | Dec | Dec
| 49 | Workflow | Internal |  | Y | 34 | 1 | Josh Twist | No | Yes | No | Regional |  | 2015-09-01 | → | C |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Nov | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Dec | Dec | Q1-16 | Q1-16
| 50 | Virtual Machines (G) | GA | 99.95 | N | NA |  | Drew McDaniel | No | No | Yes | Regional |  | 2015-09-01 | → | D |  | - |  | ü |  |  |  | ü |  | ü | Dec | [12 empty] | Q1-16
Ring 2 | 51 | BizTalk Services | GA | 99.9 | N |  |  | Harish Kumar Agarwal | No | No | Yes | Regional |  | 2015-09-01 | → | B |  | - | ü |  | ü |  | ü | ü | ü | ü | ü | ü | bar: Nov to Dec
| 52 | Data Factory | GA | 99.9 | N |  |  | Anil Manickath | No | No | No | Regional |  | 2015-09-01 | → | A |  | → | [5 empty] | ü | ü
| 53 | Mobile Engagement | GA |  | N |  |  | Karl Piteira | No | No | No | Regional |  | 2015-09-29 | ↑ | A |  | - |  |  |  | ü |  |  | ü
| 54 | Mobile Services | GA | 99.9 | N |  |  | Kirill Gavrylyuk | No | Yes |  | Regional |  | 2015-09-01 | → | C |  | - | ü |  |  |  |  | ü | ü |  |  | ü | [8 empty] | ü | ü | bar: Dec
| 55 | Operational Insights | GA | 99.9 | N |  |  | Richard Rundle | No | No |  | Regional |  | 2015-09-01 | → | A |  | - | ü | [6 empty] | ü
| 56 | Storage - Import/Export | GA | - | N |  |  | Pradnya Khadapkar | No | No | Yes | Regional |  | 2015-09-01 | → | A |  | → | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü |  | Oct | Oct | Oct | Oct | Dec | Dec |  | Nov | Nov | Nov | Nov
| 57 | Virtual Machines (A8,A9,A10,A11) | GA | 99.95 | N |  |  | Alex Sutton | No | No | Yes | Regional |  | 2015-09-01 | → | D |  | - | ü |  | ü | ü | ü | ü | ü | ü | bar: Oct
| 58 | Visual Studio Online | GA | 99.9 | N |  |  | Andrew Brenner | No | No | No | Regional |  | 2015-09-01 | → | A |  | → |  |  | ü |  | ü |  |  | ü | bar: Oct
Ring 3 | 59 | Application Insights | Preview |  | N |  |  | Dave Lubash | No | No | No | Regional |  | 2015-09-01 | → | A |  | → |  |  |  | ü
| 60 | Cloud DNS* | Preview |  | Y |  |  | Jonathan Tuliani | No | Yes |  | Global |  | 2015-09-01 | → | - |  | → |  |  | ü |  | ü | [13 empty] | Q1-16 | Q1-16 | Q1-16 | Q1-16 |  |  | Q1-16 | Q1-16
| 61 | Data Catalog | Preview |  | N |  |  | Derek Tan | [5 empty] | 2015-09-01 | → |  |  | - | ü |  |  |  |  | ü |  | ü | bar: Oct
| 62 | Data Lake Store | Approved |  | N |  |  | Raji Easwaran | [5 empty] | 2015-09-01 | → | - |  | - | Apr | ü |  | Apr |  | Apr | Jan | Apr | H1-16 | H1-16 |  | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 |  | H2-16 | H2-16 | H2-16 | H2-16 | H1-17 | H1-17 | H1-17 | H1-17 | H1-17 | H1-17
| 63 | Data Lake Analytics | Approved |  | N |  |  | Raji Easwaran | [5 empty] | 2015-09-01 | → |  |  | - | Apr | ü |  | Apr |  |  | Jan | Apr | H1-16 | H1-16 |  | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 | H2-16 |  | H2-16 | H2-16 | H2-16 | H2-16 | H1-17 | H1-17 | H1-17 | H1-17 | H1-17 | H1-17
| 64 | Dev/Test Lab | Approved |  | N |  |  | Raman Kumar | [5 empty] | 2015-09-01 | → |  |  | - | ü |  |  |  |  | ü |  | ü |  | ü
| 65 | IOT Hub | Preview |  | N |  |  | Nayana Singh | [5 empty] | 2015-09-25 | NEW |  |  |  | ü | [5 empty] | ü |  |  | ü
| 66 | Service Fabric | Preview |  | N |  | 0 | Chacko Daniel | [5 empty] | 2015-09-01 | → | - |  | - | ü | Q1-16 | Q1-16 | Q1-16 | Q1-16 | ü | Nov | Q1-16 | Nov | Nov | Q1-16 | Q1-16 | Q1-16 | Q1-16 | Q1-16 | H1-16 | H1-16 | H1-16 | Oct | ü | H1-16 | H1-16 | H1-16 | H1-16 | H1-16 | H1-16
| 67 | SQL Datawarehouse | Preview |  | N |  |  | Matt Usher | [5 empty] | 2015-09-01 | → |  |  | - | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | bar: Oct; Oct to Oct
[6 empty] | 26238 | 265

## Legend
All dates are Calendar Year (CY)
Deployed
Not Required
Planned
No plan or plan does not meet business requirements

## Changes Log
Date | Editor | Row | Change
2015-03-06 | Leon | Virtual Machines (D) | Updated Virtual Machines (D) in CA and DE to Q4
2015-03-06 | Leon | Azure Search | Azure Search GA'd on 3/5. Moved to Ring 2.
2015-03-06 | Leon | Document DB | Added owner
2015-03-06 | Leon | Operational Insights | Added owner
2015-03-06 | Leon | Workflow | Updated Workflow date in AUS to Mar.
2015-03-06 | Leon | Active Directory | Added separate row for Active Directory Premium
2015-03-06 | Leon | Power BI | Moved Power BI from Ring 2 to Ring 1 based on critieria
2015-03-07 | Leon | Scheduler | Scheduler is in Australia now, updated accordingly.
2015-03-10 | Leon | RemoteApp | Stores customer data. Moved to Ring 1
2015-03-10 | Leon | RemoteApp | Australia date brought in from April to March
2015-03-11 | Leon | Azure Redis Cache | Shared plans to be in CA, DE in December
2015-03-11 | Leon | XIO | Confirmed accelerated plan that would allow them to be in all regions this year
2015-03-12 | Leon | Notification Hubs | Updated owner to Scott Seely.
2015-03-12 | Leon | Azure Search | Shared plans to be in Japan, Australia and Brazil in July. Updated.
2015-03-12 | Leon | Operational Insights | Planned for Europe West in March. Updated.
2015-03-12 | Leon | Azure Search | Stores customer data in same region. Moved to Ring 1
2015-03-12 | Leon | Automation | In Japan East also now
2015-03-12 | Leon | Automation | Shared plans to be in BJB in Mar and SHA in July
2015-03-12 | Leon | Automation | Stores customer data. Moved to Ring 1
2015-03-12 | Leon | Workflow | Updated owner to Alok Jain
2015-03-12 | Leon | Machine Learning | Stores customer data in same region. Moved to Ring 1
2015-03-12 | Leon | Machine Learning | Shared plans for several geographies. Updated.
2015-03-12 | Leon | Storage - IE | This is GA. Updated
2015-03-12 | Leon | Storage - IE | Shared dates for Aus, Japan
2015-03-13 | Leon | Site Recovery | Shared that customer data is not stored. Moved to ring 2.
2015-03-19 | Leon | Active Directory | Canada date updated to Oct. Can be checked right now since global instance will be used.
2015-03-19 | Leon | Active Directory Premium | Canada date updated to Oct. Can be checked right now since global instance will be used.
2015-03-20 | Leon | Batch | Canada date updated to Nov. Germany to Dec
2015-03-20 | Leon | Media Services | Canada date updated to Nov. Germany to Dec
2015-03-20 | Leon | Scheduler | Canada date updated to Nov. Germany to Dec
2015-03-20 | Leon | Websites | Canada date updated to Nov. Germany to Dec
2015-03-23 | Leon | Portal - Vcurrent | Added
2015-03-23 | Leon | Portal - Ibiza | Added
2015-03-23 | Leon | Cloud DNS | Added
2015-03-24 | Leon | Backup | Updated Canada and Germany dates
2015-03-24 | Leon | StorSimple | Updated Canada and Germany dates
2015-03-24 | Leon | Multiple | Called out Global services and updated to show 'Deployed' regions only
2015-03-24 | Leon | Azure App Service | Added preview features below this suite.
2015-03-25 | Leon | CDN | Updated availability in India, Germany
2015-03-25 | Leon | Event Hubs | Updated dates for Canada, Germany
2015-03-25 | Leon | Azure Search | Will only be in one region in Aus. Updated
2015-03-25 | Leon | BizTalk | Will not be deployed to any regions moving forward
2015-03-25 | Leon | Mobile Svcs | Will not be deployed to any regions moving forward
2015-03-26 | Leon | Notification Hubs | India/Canada/Germany plans updated
2015-03-26 | Leon | RemoteApp | Available in Australia today. Updated.
2015-03-30 | Leon | Logic App | Updated owner
2015-03-30 | Leon | Mobile App | Updated owner
2015-03-30 | Leon | API App | Updated owner
2015-03-30 | Leon | API App | Available in Australia.
2015-03-30 | Leon | Mobile App | Available in Australia.
2015-03-31 | Sam | Event Hubs | Available in FF
2015-03-31 | Sam | Notification Hubs | Available in FF
2015-03-31 | Sam | Service Bus | Available in FF
2015-03-31 | Sam | Workflow | Available in FF
2015-03-31 | Sam | Media Services | Available in FF
2015-03-31 | Leon | Automation | In progress in BJB. Updated from Mar to April
2015-03-31 | Qingsu | XIO | In China East now.
2015-03-31 | Leon | Virtual Machines (D) | Plan changed from Q4 to Sep in FF
2015-03-31 | Leon | Azure Redis Cache | Plan changed from Q2 to Apr in MC
2015-03-31 | Leon | Azure Redis Cache | Plan changed from Q4 to Dec in FF
2015-03-31 | Leon | ExpressRoute | Plan changed from Q3 to June in MC
2015-03-31 | Leon | XIO | Slipped from Mar to Apr in SE Asia and Japan West
2015-03-31 | Leon | Event Hubs | Available in US North Central in March
2015-03-31 | Leon | ExpressRoute | Plan changed from Mar to June in Japan West
2015-03-31 | Leon | Stream Analytics | Plan changed from Mar to April for Japan regions
2015-03-31 | Leon | Stream Analytics | Available in Europe North in March
2015-03-31 | Leon | StorSimple | Available in Brazil
2015-04-02 | Leon | XIO | Updated with latest plans
2015-04-03 | Leon | Automation | Public preview in China
2015-04-03 | Leon | Automation | Available in China East (SHA)
2015-04-03 | Leon | Stream Analytics | Available in US West and Japan East
2015-04-03 | Leon | RemoteApp | India planned for July
2015-04-06 | Leon | Storage - Files | Added to Ring 3. This is in Public preview but by sign up/invitation only
2015-04-07 | Leon | VSO | Updated plans to be in Australia
2015-04-08 | Leon | Document DB | GA'd. Moved up to ring 1
2015-04-09 | Leon | Document DB | Updated Plans for India, Japan, Australia, US South Central, Brazil
2015-04-10 | Leon | Mobile App | Updated with plans for China, US Gov and Germany
2015-04-10 | Leon | Logic App | Updated with plans for China, US Gov and Germany
2015-04-10 | Leon | API App | Updated with plans for China, US Gov and Germany
2015-04-10 | Leon | App Service | Updated with plans for China, US Gov and Germany
2015-04-13 | Leon | Marketplace | Added to Ring 1.
2015-04-13 | Leon | Service Fabric | Added to Ring 0.
2015-04-13 | Leon | Traffic Manager | Updated date for Traffic Manager in Germany
2015-04-13 | Leon | Cloud DNS | Updated date for Cloud DNS in Germany
2015-04-14 | Qingsu | Azure Search | Updated with plans for China, US Gov
2015-04-14 | Qingsu | MFA | Updated with date for China
2015-04-14 | Qingsu | Redis Cache | Now available in China
2015-04-15 | Leon | Storage - Premium | Available in SGP and Japan West
2015-04-16 | Leon | Storage - Premium | Advanced to GA
2015-04-16 | Leon | Stream Analytics | Available in SouthEast Asia
2015-04-16 | Leon | Stream Analytics | Advanced to GA
2015-04-17 | Leon | KeyVault | Updated with dates for India, Canada and sovereign clouds
2015-04-20 | Qingsu | Batch | Updated dates for China, US Gov
2015-04-21 | Leon | Operational Insights | Available in West Europe
2015-04-21 | Leon | Machine Learning | Updated with dates for Canada, Germany, India to Dec16. Date too far out.
2015-04-21 | Leon | Automation | Updated with dates for all Geos
2015-04-22 | Leon | Virtual Machines (A8-A11) | Moved to Ring 2 as no plans to expand. Will redirect customers to D/G.
2015-04-22 | Leon | Stream Analytics | Updated plans for all Geos.
2015-04-23 | Leon | Virtual Machines (G) | Updated plans for West Europe, South East Asia
2015-04-27 | Qingsu | Azure Redis Cache | Updated FF plans from Dec to July.
2015-04-27 | Leon | HDInsight | Available in Brazil South
2015-04-28 | Leon | Media Services | Updated plans for Aus.
2015-04-28 | Leon | Stream Analytics | Available in US S Central
2015-04-29 | Leon | Azure Resource Manager | Added to Ring 0.
2015-04-30 | Leon | Stream Analytics | Available in E Asia
2015-04-30 | Qingsu | ARM | Early July
2015-05-08 | Suresh | Multiple | Updated India Services
2015-05-12 | Suresh | HDInsight | Updated India date to Aug
2015-05-12 | Suresh | Stream Analytics | Updated India date to Aug
2015-05-12 | Leon | Stream Analytics | Updated LATAM date to June
2015-05-12 | Leon | DNS | Updated dates to Q12016 for China and US Gov.
2015-05-15 | Leon | Visual Studio Online | Available in Australia East
2015-05-15 | Qingsu | Stream Analytics | Q3 to Q4 in Fairfax
2015-05-18 | Leon | Stream Analytics | Available in US North Central, Japan West
2015-05-26 | Leon | MFA | Available in US Gov
2015-05-27 | Leon | StorSimple | Available in FF
2015-05-27 | Leon | Stream Analytics | Slipped from May to June. Should be available next week.
2015-05-27 | Qingsu | AAD Premium | Mooncake date slippage: Q4 -> H2-16 due to AAD new deployment tool onboarding (ExpressV2)
2015-05-28 | Leon | Premium Storage | Available in Australia East
2015-05-28 | Leon | G-series | Slip from May to June
2015-05-29 | Leon | Media Services | Available in Australia East and South.
2015-06-03 | Leon | Backup | Available in US Central
2015-06-08 | Leon | Pilotfish | Added to Ring 0.
2015-06-09 | Leon | G-series | Updated from June to July
2015-06-09 | Leon | Search | No date for China, Sovereign clouds.
2015-06-09 | Leon | Backup | Available in US N Central, US S Central, East US 2 and Brazil South
2015-06-10 | Leon | Automation | Available in South Central US
2015-06-11 | Leon | VMs - D | Brazil slip from June to July
2015-06-11 | Leon | VMs - G | US Gov plan updated to Q1-16
2015-06-12 | Leon | Dev/Test Lab | Added Dev/Test Lab to Ring 3 (Approved but not in preview yet)
2015-06-15 | Leon | Site Recovery | LATAM slipped from June to July.
2015-06-18 | Leon | Stream Analytics | Available in US East, Australia East and Australia South East.
2015-06-20 | Leon | Active Directory | Germany - Red to Nov.
2015-06-22 | Leon | Machine Learning | Europe and APAC moved from June to Aug/Sep
2015-06-22 | Leon | Backup | Updated AWS comparison
2015-06-22 | Leon | CDN | Updated AWS comparison
2015-06-23 | Qingsu | ExpressRoute for Mooncake | June->Aug
2015-06-23 | Qingsu | MFA for Mooncake | June->July
2015-06-23 | Qingsu | Ibiza | June ->Sep
2015-06-23 | Qingsu | PowerBI | No commitement ->H2-16
2015-06-23 | Qingsu | App Service | July ->Oct
2015-06-23 | Leon | Import/Export | China slipped from June -> Aug
2015-06-24 | Leon | KeyVault | Advanced to GA
2015-06-24 | Leon | KeyVault | Available in East US 2, Central US, US S Central, US West, Brazil South, Japan East, Japan West.
2015-06-30 | Saad | ExpressRoute | Available in US Gov Virginia
2015-06-30 | Saad | Import/Export | US Gov slipped from July -> Aug
2015-06-30 | Saad | ExpressRoute | US Gov Iowa updated to Q1-16 (Jan 16)
2015-06-30 | Leon | Pilotfish | Available in US N Central and ?E Asia?
2015-06-30 | Leon | Pilotfish | Europe West slipped from June to July
2015-06-30 | Leon | CDN | LATAM slipped from June to Q4. (Pending pricing agreement with Edgecast)
2015-06-30 | Leon | Media Services | LATAM slipped from June to July.
2015-06-30 | Suresh | Virtual Machines (A1-A7) | Available in India South
2015-06-30 | Suresh | Cloud Services | Available in India South
2015-06-30 | Suresh | Storage | Available in India South, India Central and India West
2015-06-30 | Suresh | Virtual Network | Available in India South
2015-07-06 | Leon | SQL DW | Added to Ring 3 (Preview)
2015-07-07 | Leon | Site Recovery | Available in Brazil South
2015-07-08 | Qingsu | Import/Export Mooncake | July->Aug
2015-07-09 | Leon | Batch | Generally available
2015-07-10 | Leon | Search | Available in Japan West, Brazil South.
2015-07-13 | Suresh | Scheduler | Available in India South, India Central and India West
2015-07-13 | Suresh | Virtual Machines | Available in India Central and India West
2015-07-13 | Suresh | Virtual Network | Available in India Central and India West
2015-07-13 | Suresh | Cloud Services | Available in India West.
2015-07-15 | Leon | Azure Data Catalog | Entered Preview
2015-07-15 | Leon | Virtual Machines (D) | Moved from July to August. Expected 8/5.
2015-07-20 | Leon | API Management | Planned for June 2016 (Red since it does not meet business requirements)
2015-07-20 | Leon | CRM Online | Added to Ring 1.
2015-07-21 | Leon | Search | Available in Australia East
2015-07-22 | Leon | VMs(D) | Moved from July to August.
2015-07-24 | Leon | Ibiza | Updated from Sep to Q4 for China and US Gov.
2015-07-24 | Leon | App Service | Updated from Sep to Q4 for China and US Gov.
2015-07-24 | Leon | Cloud Services | Available in India Central
2015-07-27 | Leon | SQL DB | Available in India South, India Central and India West
2015-07-27 | Leon | Batch | Available in India South, India Central and India West
2015-07-28 | Leon | Power BI | Now Generally Available
2015-07-28 | Leon | Power BI | Removed preview row
2015-07-31 | Leon | Data Factory | Available in North Europe
2015-07-31 | Leon | Azure Resource Manager | July to Aug in US Gov
2015-07-31 | Leon | Redis Cache | July to Aug in US Gov
2015-07-31 | Leon | Service Bus | Available in India South, India Central and India West
2015-07-31 | Leon | Redis Cache | Available in India South, India Central and India West
2015-07-31 | Leon | Web App | July to Aug in India regions
2015-07-31 | Leon | Backup | July to Aug in India regions
2015-07-31 | Leon | Site Recovery | July to Aug in India regions
2015-07-31 | Leon | Import/Export | July to Sep in Japan and Australia
2015-07-31 | Leon | Azure Resource Manager | July to Aug in India regions
2015-07-31 | Leon | Mobile App | Q4 to Q1-16 in US Gov
2015-07-31 | Leon | Logic App | Q4 to Q1-16 in US Gov
2015-07-31 | Leon | API App | Q4 to Q1-16 in US Gov
2015-07-31 | Leon | G-series | July to Aug in West Europe
2015-08-04 | Leon | Web App | Available in India regions
2015-08-04 | Leon | Workflow | Available in India regions
2015-08-06 | Leon | Data Factory | Advanced to GA
2015-08-14 | Leon | Azure Resource Manager | Available in India regions
2015-08-14 | Leon | Event Hubs | Available in India regions
2015-08-14 | Leon | API App | Available in India regions
2015-08-14 | Leon | Virtual Machines (D) | Available in Brazil South
2015-08-18 | Leon | HDInsight | Available in India Central
2015-08-18 | Leon | Machine Learning | Available in South East Asia
2015-08-20 | Leon | G-series and GS | Available in Europe West and US West
2015-08-20 | Leon | Site Recovery | Available in US Central, US North Central, US South Central, East US2
2015-08-21 | Leon | Pilotfish | Available in Europe West
2015-08-24 | Leon | ExpressRoute | Available in India South and West.
2015-08-25 | Leon | Redis Cache | Update FF from Aug to Sep
2015-08-25 | Leon | Backup | Updated FF from Aug to Sep
2015-08-25 | Leon | Site Recovery | Updated FF from Aug to Sep
2015-08-25 | Leon | Notification Hubs | Available in India South, India Central and India West
2015-08-25 | Leon | Backup | Available in India Central
2015-08-25 | Leon | Site Recovery | Available in India Central
2015-08-26 | Qingsu | Stream Analytics | Available in China East and China North
2015-08-26 | Qingsu | Service Fabric | Moved from H12016 to Sep
2015-08-31 | Leon | Azure Resource Manager | Moved from Aug to Sep in US Gov
2015-08-31 | Leon | Web App | Moved from Aug to Sep in US Gov
2015-08-31 | Leon | KeyVault | Moved from Aug to Sep in Aus
2015-08-31 | Leon | Virtual Machines - D | Available in India South, India Central and India West
2015-08-31 | Leon | Backup | Available in India South and West.
2015-08-31 | Leon | Site Recovery | Available in India South and West.
2015-08-31 | Leon | Media Services | Moved from Aug to Sep in India regions
2015-09-02 | Leon | Document DB | Available in Australia regions
2015-09-07 | Leon | Azure Resource Manager | Available in US Gov
2015-09-08 | Leon | Stream Analytics | Available in Brazil South
2015-09-10 | Leon | Multiple | Germany dates updated
2015-09-12 | Leon | Machine Learning | Available in West Europe
2015-09-14 | Leon | Backup | Available in US Gov regions
2015-09-15 | Leon | Premium Storage | India dates updated
2015-09-17 | Leon | KeyVault | Available in Australia regions
2015-09-18 | Leon | Automation | Available in US Gov Virginia
2015-09-18 | Leon | Redis Cache | Available in US Gov regions
2015-09-20 | Leon | Virtual Machines-D | Moved from Sep to Oct in US Gov
2015-09-20 | Leon | Document DB | Available in India South, India Central and India West
2015-09-21 | Qingsu | MFA | Updated MC from Sep to Dec
2015-09-22 | Leon | Logic App | Moved to Oct in India regions
2015-09-22 | Leon | Mobile App | Moved to Oct in India regions
2015-09-22 | Leon | CDN | Moved from Sep to Dec in India regions
2015-09-22 | Leon | Media Services | Available in India South and India Central
2015-09-22 | Leon | RemoteApp | Moved from Sep to Oct in India regions
2015-09-28 | Leon | Import/Export | Moved from Sep to Oct in Japan and Australia
2015-09-28 | Leon | Import/Export | Moved from Sep to Nov in China and US Gov
2015-09-28 | Leon | Service Fabric | Available in China North
2015-09-29 | Leon | Files | Advanced to GA
2015-09-29 | Leon | Mobile Engagement | Advanced to GA
2015-09-29 | Leon | Media Services | Available in Brazil South
2015-09-29 | Leon | Search | Available in India Central
2015-09-30 | Saad | Express Route | DM is also done
2015-09-30 | Saad | EMS | Q1-16 to Q2-16 Red
2015-09-30 | Saad | Web App | Moved from Sep to Oct
2015-09-30 | Saad | Site Recovery | Moved from Sep to Oct
2015-09-30 | Leon | Ibiza | Moved from Nov to Q1-16
2015-10-02 | Leon | KeyVault | Date moved forward from H1-16 to Jan 16 in China
2015-10-08 | Leon | KeyVault | Date moved from Dec to Jan in India

## Ring Classification
Classification | Service Attributes | Availability
Ring 0 | Core Azure Infrastructure - Basic building blocks for Azure Applications | All Azure regions
Ring 1 | Required by Major* 1st party OR stores customer data as defined on the Azure trust center. AND No plans to deprecate | All Azure Geographies
Ring 2 | Generally available but not ring 0 or 1. | Established Geographies**
Ring 3 | In Preview and not required by major first party | US

## Geography Classification
Current
Taxonomy | Enterprise + Direct billed customers active | Azure Geographies
Established | 10,000+ | US, Europe
Emerging | 5,000 – 10,000 | LATAM, APAC
Incubation | 25 - 5,000 | Japan, China, Australia, US Government
Preview & Plan | <25 | India, Canada, Germany
Previous
Taxonomy | Geographies | Revenue > $100M | Data Center Prescence
Established | US, Europe | ü | ü
Emerging | APAC, LATAM, Japan, China, Australia, US Government |  | ü
Preview | India, Canada, Germany |  | Planned